## Slide 1: Aspire VN Launch Campaign Plan
Document ID: M02
Department: Marketing
Owner: Linh Tran, VN Launch Campaign Lead
Version: v0.9 draft
Effective Date: 2026-10-01
Classification: Internal
Compartments: none

## Slide 2: Objectives
Support go-live of the Aspire Corporate Card in Vietnam targeted for 2027-02-01
Recruit 150 SMEs into the VND corporate card pilot
Build brand awareness among Ho Chi Minh City finance leads
Total marketing budget: SGD 800k, Dec 2026 to Mar 2027
Notes: Project code proj_card_launch_vn. Go-live depends on SBV licensing through our local partner; the campaign plan includes a hold gate.

## Slide 3: Target SMEs in HCMC
Segment A: export-oriented SMEs in Districts 1, 3 and Thu Duc with 20-200 staff
Segment B: e-commerce and SaaS firms paying overseas ad platforms in USD
Segment C: logistics and trading firms with frequent cross-border supplier payments
Persona: finance manager or founder-CFO, aged 30-45, uses Zalo and LinkedIn daily
Notes: Segment A is expected to deliver about 60 of the 150 pilot SMEs.

## Slide 4: Positioning and Message
Spend control for growing Vietnamese businesses: one card, every team, full visibility
Proof points: real-time limits, VND and USD spend, expense capture in Aspire Spend
Tagline in Vietnamese reviewed by local counsel and Brand Studio
All claims comply with Brand Guidelines v2026 and SBV advertising rules
Notes: No cashback claims in VN until pricing is approved locally.

## Slide 5: Channels
LinkedIn and Facebook paid campaigns targeting HCMC finance roles
Zalo Official Account with onboarding flow and chatbot
Partner channel: co-marketing with the local partner bank and 3 accounting firms
Events: 2 CFO breakfast roundtables and 1 launch event in HCMC
Content: Vietnamese-language guides on cross-border payments
Notes: Paid social is the largest line, with partner channel expected to have the lowest CAC.

## Slide 6: Budget Split (SGD 800k)
Paid digital: SGD 320k (40%)
Events and roadshows: SGD 160k (20%)
Partner co-marketing: SGD 120k (15%)
Content, localisation and creative: SGD 100k (12.5%)
PR and influencers: SGD 60k (7.5%); contingency: SGD 40k (5%)
Notes: Contingency of SGD 40k is released only by the Marketing Manager with CFO notification.

## Slide 7: Timeline Dec 2026 to Mar 2027
Dec 2026: creative, localisation, landing page and waitlist opens
Jan 2027: teaser campaign, partner briefings, 2 roundtables
1 Feb 2027: go-live and launch event; pilot onboarding begins
Feb-Mar 2027: performance push, case studies, referral incentives
End Mar 2027: pilot review and decision on full rollout
Notes: If SBV approval slips, the go-live burst moves but the waitlist stays live.

## Slide 8: KPIs
150 pilot SMEs onboarded by 2027-03-31
Blended CAC target: SGD 2,400 per activated SME (SGD 360k of acquisition spend plus partner costs)
6,000 waitlist sign-ups and 15% waitlist-to-application conversion
60% of pilot SMEs issue at least 3 cards within 30 days
NPS of 40 or higher at pilot end
Notes: CAC is calculated on activated accounts, not sign-ups.

## Slide 9: Risks and Mitigations
Licensing delay: keep waitlist-only mode and hold paid spend until approval
Regulatory wording issues: local counsel review within 3 business days per asset
Low trust in a new brand: lean on partner bank co-branding and testimonials
Currency volatility affecting budget: budget fixed in SGD, 5% FX buffer
Localisation quality: native reviewer sign-off on every asset
Notes: Risk owner is the VN Launch campaign lead; reviewed weekly.