## About
Document ID | J03
Department | Compliance
Owner | Nur Aisyah, Head of Regulatory Affairs
Version | v0.6
Effective Date | 2026-10-01
Classification | Internal
Compartments | none

## Evidence Index
ID | Evidence / control | MAS inspection area | Owner | Status | Location
E-01 | AML/CFT policy v4.2 | Governance and oversight | Compliance | Complete | Compliance SharePoint /aml/policy
E-02 | Board and Risk Committee minutes 2026 (AML agenda items) | Governance and oversight | Company Secretary | Complete | Legal repository /board/2026
E-03 | Organisation chart and MLRO appointment letter | Governance and oversight | HR | Complete | HR drive /orgchart
E-04 | Three lines of defence charter | Governance and oversight | Risk | Complete | Risk wiki
E-05 | Enterprise-wide AML/CFT risk assessment 2026 | Risk assessment | Compliance | In review | Compliance SharePoint /ewra
E-06 | Customer risk rating methodology | Risk assessment | Compliance | Complete | Compliance SharePoint /crr
E-07 | Product risk assessments (Card, Pay, Account) | Risk assessment | Product | In progress | Product wiki
E-08 | New product approval records, 2025-2026 | Risk assessment | Product | Complete | Product wiki /npa
E-09 | KYC standard operating procedure | Customer due diligence / KYC | KYC Operations | Complete | Ops wiki /kyc
E-10 | Sample of 60 onboarding files with CDD evidence | Customer due diligence / KYC | KYC Operations | In progress | KYC case system export
E-11 | High-risk customer EDD file sample (25) | Customer due diligence / KYC | KYC Operations | In progress | KYC case system export
E-12 | Ongoing review completion statistics | Customer due diligence / KYC | KYC Operations | Complete | BI dashboard AML-07
E-13 | Beneficial ownership verification procedure | Customer due diligence / KYC | KYC Operations | Complete | Ops wiki /ubo
E-14 | Sentinel rule inventory and thresholds | Transaction monitoring | Financial Crime Ops | Complete | Compliance SharePoint /tm
E-15 | Sentinel tuning and below-the-line testing reports | Transaction monitoring | Financial Crime Ops | In review | Compliance SharePoint /tm/tuning
E-16 | Alert backlog and ageing report (monthly) | Transaction monitoring | Financial Crime Ops | Complete | BI dashboard AML-02
E-17 | Transaction monitoring replacement plan (proj_aml_upgrade) | Transaction monitoring | Engineering | Complete | Project folder proj_aml_upgrade
E-18 | Model validation report for monitoring scenarios | Transaction monitoring | Risk | Not started | TBD
E-19 | Sanctions screening procedure and list update logs | Sanctions screening | Financial Crime Ops | Complete | Compliance SharePoint /sanctions
E-20 | Screening hit disposition sample (100 cases) | Sanctions screening | Financial Crime Ops | In progress | Case system export
E-21 | Screening vendor SLA and uptime report | Sanctions screening | Procurement | Complete | Vendor register
E-22 | STR filing procedure and escalation matrix | STR reporting | MLRO Office | Complete | Compliance SharePoint /str
E-23 | STR register 2025-2026 (counts and timeliness) | STR reporting | MLRO Office | In review | Restricted drive (MLRO)
E-24 | Tipping-off safeguards guidance | STR reporting | MLRO Office | Complete | Compliance SharePoint /str
E-25 | AML/CFT training curriculum and completion rates | Training | Compliance | Complete | LMS report
E-26 | Role-based training for KYC and Ops teams | Training | Compliance | In progress | LMS report
E-27 | Record retention schedule (5 years) | Record keeping | Legal | Complete | Legal repository /retention
E-28 | Evidence of record retrieval test | Record keeping | Engineering | In progress | Engineering wiki
E-29 | Internal audit report on AML/CFT 2025 and remediation tracker | Governance and oversight | Internal Audit | Complete | Audit portal
E-30 | Independent testing of AML/CFT controls (compliance monitoring plan) | Governance and oversight | Compliance | In review | Compliance SharePoint /monitoring

## Open Requests
Request ID | Date received | MAS request | Mapped area | Owner | Due | Status
R-01 | 2026-10-05 | List of all high-risk customers and EDD status | Customer due diligence / KYC | KYC Operations | 2026-10-16 | Open
R-02 | 2026-10-05 | Board minutes discussing AML for last 12 months | Governance and oversight | Company Secretary | 2026-10-14 | In progress
R-03 | 2026-10-06 | Sentinel alert ageing by month | Transaction monitoring | Financial Crime Ops | 2026-10-15 | In progress
R-04 | 2026-10-06 | Sanctions screening configuration and fuzzy matching thresholds | Sanctions screening | Financial Crime Ops | 2026-10-20 | Open
R-05 | 2026-10-07 | Walkthrough of onboarding for a corporate customer | Customer due diligence / KYC | KYC Operations | 2026-10-22 | Scheduled
R-06 | 2026-10-07 | STR timeliness statistics | STR reporting | MLRO Office | 2026-10-17 | Open
R-07 | 2026-10-08 | Model validation evidence for monitoring | Transaction monitoring | Risk | 2026-10-30 | At risk
R-08 | 2026-10-08 | Training attendance for senior management | Training | Compliance | 2026-10-19 | In progress
R-09 | 2026-10-09 | Plans for the replacement of the monitoring engine | Transaction monitoring | Engineering | 2026-10-21 | In progress
R-10 | 2026-10-09 | Outsourcing register for AML tools | Governance and oversight | Procurement | 2026-10-23 | Open
R-11 | 2026-10-12 | Customer risk rating methodology and overrides | Risk assessment | Compliance | 2026-10-26 | Open
R-12 | 2026-10-12 | Record retrieval test results | Record keeping | Engineering | 2026-10-28 | Open
R-13 | 2026-10-13 | Internal audit follow-up status | Governance and oversight | Internal Audit | 2026-10-27 | In progress
R-14 | 2026-10-14 | Sample of 25 declined onboarding cases | Customer due diligence / KYC | KYC Operations | 2026-10-29 | Open
R-15 | 2026-10-15 | Interview slots with MLRO and Head of KYC | Governance and oversight | Compliance | 2026-11-03 | Scheduled