## About
Document ID | J06
Department | Corporate Development
Owner | Jonathan Seah, VP Corporate Development
Version | v1.0
Effective Date | 2026-10-08
Classification | Confidential
Compartments | none

## Risk Register
Risk ID | Category | Risk Description | Likelihood | Impact | Rating | Owner | Mitigation | Status
R-001 | Financial | PayNest customer concentration: top 3 = 46% revenue, largest = 21%. Revenue loss if key customer churns post-acquisition. | High | High | Red | VP Finance | Negotiate multi-year contracts with top 3 customers as condition of signing; retention bonus to account managers. | Open
R-002 | Compliance | AML/CFT programme gaps: 1900 stale alerts, no onboarding screening for corporate UBOs, EWRA outdated since 2024. Risk of MAS enforcement post-acquisition. | High | High | Red | MLRO | SGD 1.2-1.8M remediation budget over 12 months via proj_aml_upgrade; MAS voluntary disclosure before completion. | Open
R-003 | Legal | Copyright claim from former contractor on reconciliation module. Exposure SGD 150k-400k. | Medium | Medium | Amber | Legal Counsel | Escrow 400k at signing; settle or defend within 6 months. | Open
R-004 | Legal | Change-of-control termination clauses in 2 customer contracts (17% of revenue). | Medium | High | Amber | Legal Counsel | Obtain waivers before completion; price adjustment if not obtained. | Open
R-005 | Technology | Monolithic Java app, single-region, RPO 24h. Integration risk and operational continuity during migration. | Medium | High | Amber | CTO | Phase migration over 9 months; maintain parallel run for 3 months; hot standby in second region. | Open
R-006 | Technology | 2 unresolved high-severity penetration test findings in core payment module. | Medium | Medium | Amber | Head of Security | Remediate before go-live; independent re-test required. | Open
R-007 | People | Key-person dependency: 2 engineers hold all core ledger knowledge. | High | High | Red | VP Engineering | Retention packages (SGD 600k total, vesting 24 months); knowledge transfer plan within 90 days. | Open
R-008 | People | MLRO also heads operations — conflict of interest and capacity risk. | Medium | Medium | Amber | COO | Separate MLRO role post-acquisition; hire replacement within 6 months. | Open
R-009 | Financial | Cash runway 7 months without funding; acquisition must close before Q2 2027 or PayNest needs bridge financing. | High | High | Red | VP Finance | Signing target 2026-12-15; bridge facility covenant max leverage 3.5x EBITDA as backup. | Open
R-010 | Strategic | Integration cost overrun: estimated 9 months / 6 FTE but synergy capture (SGD 20M PV) depends on cross-sell execution. | Medium | High | Amber | Steering Committee | Stage-gate reviews at month 3, 6, 9; kill switch if synergies < 50% of plan by month 12. | Open

## Residual Risk Summary
Category | Red Risks | Amber Risks | Total
Financial | 2 | 0 | 2
Compliance | 1 | 0 | 1
Legal | 0 | 2 | 2
Technology | 0 | 2 | 2
People | 1 | 1 | 2
Strategic | 0 | 1 | 1
TOTAL | 4 | 6 | 10
Overall residual risk rating | HIGH
Recommendation | Proceed with acquisition subject to: (1) key-customer waivers, (2) AML remediation plan agreed with MAS, (3) retention packages signed, (4) escrow for copyright claim. Price adjustment of SGD 1.5M for AML remediation already reflected in indicative range.